## New product development
No | Milestones and Tasks | Done (Y/N) | Budget | Responsible person | January |  |  |  | February |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | Validation of a new product idea |  | 0 | bar: October 40 to December 52
1.1 | New product ideas generated and screened based on customer jobs, problems and gains |  | 0
1.2 | Market analysis done: target market size and competitive situation |  | 0
1.3 | Target customer feedback received for problem/solution verification |  | 0
1.4 | Technical feasibility of a new product confirmed |  | 0
1.5 | Product - market fit verification (target price confirmed) |  | 0
1.6 | Business model outlined |  | 0
1.7 | Funds needed for product development secured |  | 0
2 | Concept design of a new product |  | 0
2.1 | Key requirements and primary features identified |  | 0
2.2 | Industrial design and technical architecture (mechanical, hardware, firmware, etc.) confirmed |  | 0
2.3 | Initial regulatory and legal plan prepared |  | 0
2.4 | Key components and materials selected |  | 0
2.5 | Product costs estimated |  | 0
2.6 | Marketing images and animations (for investor presentations and pre-sales) prepared |  | 0
3 | Detailed engineering |  | 0
3.1 | Industrial design analysis done |  | 0
3.2 | Detailed technical design and documentation for prototypes and final product prepared |  | 0
3.3 | List of components and material for prototyping and mass production done |  | 0
3.4 | Key components and suppliers selected |  | 0
3.5 | Detailed cost estimated |  | 0
3.6 | Obtain regulatory appovals if required |  | 0
3.7 | Apply for patents if needed |  | 0
3.8 | Market feasibility study updated based on estimated production costs |  | 0
4 | Pre-production testing |  | 0
4.1 | Parts and materials ordered |  | 0
4.2 | The prototype built/assembled |  | 0
4.3 | Product in-house testing (mechanical, hardware, firmware, etc.) done |  | 0
4.4 | Usability and user experience testing done |  | 0
4.5 | Testing reports, conclusions and decisions made |  | 0
4.6 | Risks re-assessed, risk reversal plan prepared |  | 0
4.7 | Documentation for mass production ready |  | 0
4.8 | Marketing images and animations upgraded |  | 0
5 | Manufacturing and delivery |  | 0
5.1 | Product modifications and upgrades if needed |  | 0
5.2 | Documentation updates |  | 0
5.3 | Trial production run conducted |  | 0
5.4 | Vendor support agreements/process finalised |  | 0
5.5 | Parts and materials for mass production ordered |  | 0
5.6 | Manufacturing schedule confirmed |  | 0
5.7 | Quality testing co-ordination |  | 0
5.8 | Develop packagind and logistical systems |  | 0
5.9 | Product delivery to distribution channels scheduled |  | 0
6 | Marketing plan and implementation |  | 0
6.1 | Pricing and positioning strategy |  | 0
6.2 | Distribution startegy |  | 0
6.3 | Marketing materials for sales (packaging, labels, user manuals etc.) |  | 0
6.4 | Marketing plan (for product communication amd promotion) confirmed |  | 0
Total budget |  |  | 0 |  | January 1: 0; February 5: 0; March 10: 0; April 14: 0; May 18: 0; June 23: 0; July 28: 0; August 32: 0; September 36: 0; October 40: 0; November 44: 0; December 48: 0